## All_WMD_Prjcts_2010-present
District | Project # or ID number | Fiscal Year | County | Entity Alias | Project Type | Project Title | Actual Project Cost/ Est. Project Cost1 | Actual Funding/ Approved Funding1 | Water Savings (MGY)2 | Water Savings (GPD) | Number of Implementations1 | Cost effectiveness per Kgal | Status | Is project a quantified BMP? Yes / No | Comments | Background
SFWMD | - | 2011 | Orange | Orange County Utilities | Indoor plumbing | Commercial Showerhead Retrofit | 48011.28 | 23822.45 | 57.85 | 158493.1507 | 16443 | 0.03 | Closed | yes | Due to lower fixture costs, project exceeded original estimates. Actual installations, 5,795 showerheads (188%) and 10,648 aerators (307%) | Purchase, distribute and verify installation of 3,075 commercial grade 1.5 gpm fixed and/or handheld showerheads, and 3,465 commercial grade 1 gpm faucet aerators in three commercial properties located along the I-4 corridor.
SFWMD | - | 2012 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33639.6 | 14500 | 2.28 | 6246.5753 | 217 | 0.62 | Closed | yes | Project is 100% complete. Project exceeded 200 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of an EPA WaterSense high efficiency toilet, on participants utility bill.
SFWMD | - | 2013 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program | 40000 | 20000 | 3.87 | 10602.7397 | 320 | 0.44 | Closed | yes | 100% complete. | Approve, process, and apply 320 (up to) $125 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SFWMD | - | 2013 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 18451.28 | 9000 | 1.14 | 3123.2877 | 114 | 0.68 | Closed | yes | 100% complete. | Approve, process, and apply 100 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet, with a limit of one (1) per residential dwelling unit, on participants’ utility bill
SFWMD | - | 2014 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 2.5 | 6849.3151 | 207 | 0.51 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and apply 207 (up to) $145 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SFWMD | - | 2015 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33015.61 | 16500 | 2.3 | 6301.3699 | 224 | 0.61 | Closed | yes | 100% complete. Processed 224 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet with a UNAR Map rating above 400 grams per flush, with a limit of one (1) per residential dwelling unit, on participants' utility bill
SFWMD | - | 2015 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 1.25 | 3424.6575 | 207 | 1.01 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and pay 207 rebates at $145 high efficiency toilet, with a limit of two (2) per eligible residential dwelling units within the Toho Water Authority service area
SFWMD | WC-2010 | 2017-2018 | Osceola | Toho Water Authority | ALFDs | Automatic Line Flushing Devices | 200000 | 76500 | 23.2 | 63561.6438 | 30 | 1.1 | On Schedule | no | Contract has not been executed for this project | Install 30 automatic line flushing devices at computer modeled locations with high water age, thereby maintaining high water quality and reducing the amount of water wasted during flushing activities.
SFWMD | WC-2015 | 2017-2018 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 47000 | 23500 | 3.42 | 9369.863 | 300 | 0.58 | On Schedule | yes | Contract has not been executed for this project | This program will provide 300 rebates of $145 each to homes within the City of St. Cloud service area toward the purchase and installation of any WaterSense HET and all associated hardware.
SFWMD | WC-2023 | 2017-2018 | Orange | Orange County Utilities | Software | Water Conservation Software Technology Project for Southwest Orange County | 169981 | 50990 | 162.6 | 445479.4521 | 0 | 1.08 | On Schedule | no | Contract has not been executed for this project | Orange County Utilities will contract with WaterSmart Software Inc. to implement software that combines technology and community-based social marketing to reduce potable water consumption of 24,283 households.
SFWMD | WC-2027 | 2017-2018 | Polk | Polk County BOCC | Software | Water Conservation Software Technology for Oak Hills water use area | 205920 | 60000 | 5.2 | 14246.5753 | 0 | 3.3 | On Schedule | no | Contract has not been executed for this project | Installation of AMI hardware and a software component for leak notification, water use comparison, historical use, threshold alarms, 2-way messaging between utility and customers, and report generation.
[6 empty] | SFWMD Total | 856048.77 | 324812.45 | 265.61 | 727698.6301 | 18062
SWFWMD | N112 | 2010 | Polk | Lakeland | Indoor Pluming | Toilet Rebate Program | 143702.3 | 70097.62 | 8.6279 | 23638 | 753 | 1.01 | 2011-07-19 | yes | complete | average savings of 31.4 gal per per day per fixture
SWFWMD | N221 | 2010 | Polk | Winter Haven | Irrigation | Smart Irrigation Controller Pilot Project | 7900 | 3950 | 7.8413 | 21483 | 12 | 0.09 | 2012-10-26 | yes | complete | low participation, only 12 of expected 50 SMS were installed. A single contractor was hired to install the SMS
SWFWMD | N249 | 2011 | Polk | Frostproof | Indoor Pluming | Toilet Rebate Program | 1954 | 977 | 0.1971 | 540 | 20 | 1.16 | 2013-10-15 | yes | complete | low participation, only 20 of expected 50 rebates were done.
SWFWMD | N314 | 2011 | Polk | Lake Alfred | Indoor Pluming | Toilet Rebate Program/DIY | 16200 | 8100 | 2.8488 | 7805 | 557 | 0.57 | 2013-10-24 | yes | complete | high participation, 57 of expected 50 rebates. Also 500 conservation kits (showerhead, aerators)
SWFWMD | N363 | 2012 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 1 | 41378 | 20689 | 10.646 | 29167 | 211 | 0.95 | 2015-12-31 | yes | complete | low participation, 211 of expected 1,100 irrigation evals. Contractor, and participation issues. An averagae of 138 gpd savings at each home based on final report 1 year pre and post monitoring. 287 conservation kits were also distributed.
SWFWMD | N613 | 2015 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 2 | 44170 | 22085 | 11.899 | 32600 | 222 | 0.84 | 2016-08-31 | yes | Ongoing | costs are $155 per evaluation plus $75 for rain sensor install.
SWFWMD | N714 | 2016 | Polk | Polk County Utilities | Irrigation | Landscape and irrigation evaluation Program | 55000 | 27500 | 10.22 | 28000 | 500 | 1.31 | 2018-11-30 | yes | Ongoing | 200 irrigation system evaluations, estimated savings is 140 gpd each, cost is $200 each. Approximately 100 rain sensor devices installed at $75 each. Also included are educational materials, program promotion, and surveys necessary to ensure the success of the program. Approximately 200 conservation kits will also be provided $10 each.
SWFWMD | N716 | 2016 | Polk | Polk County Utilities | software AMA | Customer Portal Pilot Project | 20000 | 10000 | 32.85 | 90000 | 5000 | 0.06 | 2018-03-01 | no | Ongoing | The project consists of a pilot program for an online software program that will enable effective distribution of conservation information. 5,000 accounts
SWFWMD | N820 | 2017 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation program | 82800 | 41400 | 15.33 | 42000 | 300 | 1.31 |  | yes | Contract has not been executed for this project | 300 irrigation system evaluations. Approximately 150 rain sensor devices installed. Also included are educational materials, program promotion, follow-up evaluations, and surveys necessary to ensure the success of the program. Approximately 300 conservation kits
SWFWMD | N814 | 2017 | Polk | Polk County Utilities | software AMA | Customer portal project | 300000 | 150000 | 153.47 | 420465.7534 | 60000 | 1.95 |  | no | Contract has not been executed for this project | Full implementation of an online software program that will enable more effective distribution of conservation information and activities. This also includes a utility side dashboard. The software and promotion material will be utility wide (approximately 60,000 accounts) for approximately one year. The demand reduction of approximatly 3%
SWFWMD | P921 | 2017 | Polk | PRWC | Indoor Pluming | indoor retrofit | 242550 | 121275 | 31.89 | 87370 | 3135 | 0.48 | 2019-10-01 | yes | Contract has not been executed for this project | FDEP funded project. 1,830 toilet rebates to replace 3.5 gpf or higher models with WaterSense labeled fixtures (1.28 gpf). 1,305 conservation kits to be distributed to homeowners.
SWFWMD | P920 | 2017 | Polk | PRWC | Irrigation | outdoor BMPs | 332150 | 166075 | 19.0895 | 52300 | 872 | 1.8 | 2019-10-02 | yes | Contract has not been executed for this project | FDEP funded project. 49 FFL rebates to change high water-use landscapes into a Florida Friendly area that requires minimal irrigation and chemicals; 229 smart irrigation (ET) controllers installed by a licensed contractor and education on proper unit operation; 594 wireless rain sensors
SWFWMD | P922 | 2017 | Polk | PRWC | FL waterstar rebates | Florida water star rebates | 700000 | 350000 | 24.1502 | 66165 | 500 | 2.02 | 2019-10-03 | no | Contract has not been executed for this project | FDEP funded project. 500 rebates to be distributed to new home builders within Polk County who build homes to Florida Water Star standards and submits proof of Water Star certification. $700 rebate per home
[6 empty] | SWFWMD Total | 1987804.3 | 992148.62 | 329.0598 | 901533.7534 | 72082
SJRWMD | 27338 | 2012 | Orange | City of Ocoee | AMI | Strategic Water Conservation | 132367 | 66184 | 3.1 | 8493.1507 | 390 | 5.03 | Closed | No | 7-11% reduction in neighborhoods with meters predicted. | https://www.youtube.com/watch?v=80joid0XJn4 20 yr life on meters. Contract required 3 years data pre and post
SJRWMD | 27285 | 2012 | Orange | City of Apopka | Irrigation | Rebate to 100 customers to install ET controllers | 35000 | 17500 | 1.3 | 3561.6438 | 100 | 1.58 | Closed | Yes | 3 yr pre post data showed 35% - 50% reduction/month
SJRWMD | 27287 | 2012 | Orange | City of Apopka | Irrig.Enforcement | Landscape implementation Ordinance Implementation | 64000 | 32000 |  | 0 |  | NA | Closed | No | 3 year pre and post data but no analysis. | Scope included assistance to city to identify violation, work with homeowners on reason and perform audits. 3 yr pre and post data.3/31/13 completion.
SJRWMD | 25435 | 2012 | Orange | Orange County | Irrigation | Smart controller study | 230000 | 100000 |  | 0 |  | NA | Closed | Yes | Contract paid out | Results show 30 - 60% savings
SJRWMD | 27288 | 2012 | Orange | City of Apopka | AMI | AMI implementation Program | 79450 | 39725 |  | 0 |  | NA | Closed | No | AMI Software update and report analysis | No pre and post data required.
SJRWMD | 26804 | 2012 | Lake | City of Groveland | Outreach | Irrigation Rule enforcement | 98460 | 48230 |  | 0 |  | NA | Closed | No | Consumption data not submittedin this contract. | Contract was to do irrigation enforcement and education.
SJRWMD | 28091 | 2014 | Orange | OCU | Irrigation | Nozzle replacement | 94350 | 31135 | 24 | 65753.4247 | 143 | NA | Closed | No | 5000 nozzles in 143 residences installed by 9/15 | No pre and post data required.
SJRWMD | 26655 | 2015 | Seminole | City of Sanford | AMR | Installation of meters and software | 490000 | 245000 |  | 0 |  | NA | Closed | No | UF report on results Dr Heaney. | 1.7mgd at a cost of $8.5 million 15 yr useful life 11% reduction in water loss.
SJRWMD | 27296 | 2015 | Seminole | Seminole County | Indoor Pluming | Indoor Plumbing Rebate Program | 93004 | 46502.4 | 4.2 | 11506.8493 | 939 | 1.4 | Closed | yes | completed
SJRWMD | 28474 | 2016 | Orange | City of Apopka | Irrigation | ET controllers, nozzles landscapes | 140176 | 70088 |  | 0 |  | 1.08 | Open | Yes | 3 yr pre and past data will be submitted. | 36.64% savings predicted based on pilot phase.
SJRWMD | 28461 | 2016 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 111470 | 55735 |  | 0 | 500 | 3.38 | Open | No | Meter replacement only , no software
SJRWMD |  | 2016 | Orange | OCU | Indoor Pluming | Toilet retrofit | 20000 | 10000 | 1.7 | 4657.5342 | 200 | 0.8 | Open | Yes | Start in fall 2016 200 toilets replaced | should end by 9/17
SJRWMD |  | 2016 | Orange | OCU | Indoor outdoor | Waterwise Neighbor Program | 21830 | 10915 | 6.1 | 16712.3288 | 100 | 0.78 | Open | Yes | starts in Fall 100 homes targeted in Wekiva basin
SJRWMD | 28424 | 2016 | Orange | OCU | Irrigation | Rainsensor Replacement Project | 97.945 | 49150 | 35.73 | 97890.411 | 1100 | 1 | Open | No | replace 1,100 rainsensors predicts 15K/month | $107.25mg for the life of the devise
SJRWMD | 28423 | 2016 | Orange | OCU | software AMA | Water$mart Customers Conserve | 224668 | 112334 | 134.9 | 369589.0411 | 30000 | 0.36 | Open | No | Community based social marketing to reduce use. | 4.9% savings expected
SJRWMD |  | 2017 | Orange | City of Apopka | Irrigation | Nozzle replacement | 140000 | 70000 | 44.5 | 121917.8082 | 200 | 0.832 | Open | No | Expect 30 - 50% savings over 200 plus audits. | based on cost shar eapplication
SJRWMD |  | 2017 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 2230565.4 | 1115283 | 153.3 | 420000 | 9000 | 1.1 | Open | No | Expansion of existing AMI program which has proven successful to engage homeowners to conserve.
SJRWMD |  | 2017 | Orange | OCU | Whole house | Waterwise Neighbor Retrofit | 74808 | 37404 | 9.9 | 27123.2877 | 300 | 6.01 | Open | Yes | Retrofit high water users indoors and out | Pre and post water use data will be required.
SJRWMD |  | 2017 | Orange | OCU | Whole House | Waterwise Neighbor NEW | 271962.5 | 135981.25 | 30.2 | 82739.726 | 500 | 3.75 | Open | Yes | Partner with builders to build water efficient homes | 82,967 gpd referenced in application so 30.2 MGY.
SJRWMD | 27269 | 2017 | Orange | Winter Garden | AMR implementation | AMR meter replacement | 400000 | 200000 | 14.3 | 39178.0822 | 1187 | 2.33 | Open | No | Expand existing AMR to more homes
[6 empty] | SJRWMD Total | 4952208.845 | 2493166.65 | 463.23 | 1269123.2877 | 44659
[6 empty] | All Districts Total | 7796061.915 | 3810127.72 | 1057.8998 | 2898355.6712 | 134803
Summary
[6 empty] | 2010 - 2014 | 1114878.46 | 520910.07 | 126.201 | 345756.2877 | 19487
[6 empty] | 2015 and onward | 6165232.845 | 3097717.65 | 896.3288 | 2455695.274 | 114555
Pace of projects 2015 onward
[6 empty] | average per year for the last 3 years | 2055077.615 | 1032572.55 | 298.7763 | 818565.0913 | 38185
[6 empty] | average pace X 20 years | 41101552.3 | 20651451 | 5975.5252 | 16371301.8265 | 763700

## modified
District | Project # or ID number | Fiscal Year | County | Entity Alias | Project Type | Project Title | Actual Project Cost/ Est. Project Cost1 | Actual Funding/ Approved Funding1 | Water Savings (MGY)2 | Water Savings (GPD) | Number of Implementations1 | Cost effectiveness per Kgal | Status | Is project a quantified BMP? Yes / No | Comments | Background
SWFWMD | N112 | 2010 | Polk | Lakeland | Indoor Pluming | Toilet Rebate Program | 143702.3 | 70097.62 | 8.6279 | 23638 | 753 | 1.01 | 2011-07-19 | yes | complete | average savings of 31.4 gal per per day per fixture
SWFWMD | N221 | 2010 | Polk | Winter Haven | Irrigation | Smart Irrigation Controller Pilot Project | 7900 | 3950 | 7.8413 | 21483 | 12 | 0.09 | 2012-10-26 | yes | complete | low participation, only 12 of expected 50 SMS were installed. A single contractor was hired to install the SMS
SFWMD | - | 2011 | Orange | Orange County Utilities | Indoor plumbing | Commercial Showerhead Retrofit | 48011.28 | 23822.45 | 57.85 | 158493.1507 | 16443 | 0.03 | Closed | yes | Due to lower fixture costs, project exceeded original estimates. Actual installations, 5,795 showerheads (188%) and 10,648 aerators (307%) | Purchase, distribute and verify installation of 3,075 commercial grade 1.5 gpm fixed and/or handheld showerheads, and 3,465 commercial grade 1 gpm faucet aerators in three commercial properties located along the I-4 corridor.
SWFWMD | N249 | 2011 | Polk | Frostproof | Indoor Pluming | Toilet Rebate Program | 1954 | 977 | 0.1971 | 540 | 20 | 1.16 | 2013-10-15 | yes | complete | low participation, only 20 of expected 50 rebates were done.
SWFWMD | N314 | 2011 | Polk | Lake Alfred | Indoor Pluming | Toilet Rebate Program/DIY | 16200 | 8100 | 2.8488 | 7805 | 557 | 0.57 | 2013-10-24 | yes | complete | high participation, 57 of expected 50 rebates. Also 500 conservation kits (showerhead, aerators)
SFWMD | - | 2012 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33639.6 | 14500 | 2.28 | 6246.5753 | 217 | 0.62 | Closed | yes | Project is 100% complete. Project exceeded 200 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of an EPA WaterSense high efficiency toilet, on participants utility bill.
SWFWMD | N363 | 2012 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 1 | 41378 | 20689 | 10.646 | 29167 | 211 | 0.95 | 2015-12-31 | yes | complete | low participation, 211 of expected 1,100 irrigation evals. Contractor, and participation issues. An averagae of 138 gpd savings at each home based on final report 1 year pre and post monitoring. 287 conservation kits were also distributed.
SJRWMD | 27338 | 2012 | Orange | City of Ocoee | AMI | Installed smart meters educated public to monitor use | 132367 | 66184 | 3.1 | 8493.1507 | 390 | 5.03 | Closed | No | 7-11% reduction in neighborhoods with meters. | https://www.youtube.com/watch?v=80joid0XJn4 20 yr life on meters. Contract required 3 years data pre and post
SJRWMD | 27285 | 2012 | Orange | City of Apopka | Irrigation | Rebate to 100 customers to install ET controllers | 35000 | 17500 | 1.3 | 3561.6438 | 100 | 1.58 | Closed | yes | 3 yr pre post data showed 35% - 50% reduction/month
SJRWMD | 27287 | 2012 | Orange | City of Apopka | Irrig.Enforcement | Landscape implementation Ordinance Implementation | 64000 | 32000 |  | 0 |  | NA | Closed | No | 3 year pre and post data but no analysis. | Scope included assistance to city to identify violation, work with homeowners on reason and perform audits. 3 yr pre and post data.3/31/13 completion.
SJRWMD | 25435 | 2012 | Orange | Orange County | Irrigation | Smart controller study | 230000 | 100000 |  | 0 |  | NA | Closed | yes | Contract paid out | Results show 30 - 60% savings
SJRWMD | 27288 | 2012 | Orange | City of Apopka | AMI | AMI implementation Program | 79450 | 39725 |  | 0 |  | NA | Closed | No | AMI Software update and report analysis
SJRWMD | 26804 | 2012 | Lake | City of Groveland | Outreach | Irrigation Rule enforcement | 98460 | 48230 |  | 0 |  | NA | closed | No | Consumption data not submittedin this contract. | Contract was to do irrigation enforcement and education.
SFWMD | - | 2013 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program | 40000 | 20000 | 3.87 | 10602.7397 | 320 | 0.44 | Closed | yes | 100% complete. | Approve, process, and apply 320 (up to) $125 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SFWMD | - | 2013 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 18451.28 | 9000 | 1.14 | 3123.2877 | 114 | 0.68 | Closed | yes | 100% complete. | Approve, process, and apply 100 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet, with a limit of one (1) per residential dwelling unit, on participants’ utility bill
SFWMD | - | 2014 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 2.5 | 6849.3151 | 207 | 0.51 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and apply 207 (up to) $145 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SJRWMD | 28091 | 2014 | Orange | OCU | Irrigation | Nozzle replacement | 94350 | 31135 | 24 | 65753.4247 | 143 | NA | Closed | No | 5000 nozzles in 143 residences installed by 9/15 | No pre and post data required.
SFWMD | - | 2015 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33015.61 | 16500 | 2.3 | 6301.3699 | 224 | 0.61 | Closed | yes | 100% complete. Processed 224 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet with a UNAR Map rating above 400 grams per flush, with a limit of one (1) per residential dwelling unit, on participants' utility bill
SFWMD | - | 2015 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 1.25 | 3424.6575 | 207 | 1.01 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and pay 207 rebates at $145 high efficiency toilet, with a limit of two (2) per eligible residential dwelling units within the Toho Water Authority service area
SWFWMD | N613 | 2015 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 2 | 44170 | 22085 | 11.899 | 32600 | 222 | 0.84 | 2016-08-31 | yes | Ongoing | costs are $155 per evaluation plus $75 for rain sensor install.
SJRWMD | 26655 | 2015 | Seminole | City of Sanford | AMR | Installation of meters and software | 490000 | 245000 |  | 0 |  | NA | closed | No | UF report on results Dr Heaney. | 1.7mgd at a cost of $8.5 million 15 yr useful life 11% reduction in water loss.
SJRWMD | 27296 | 2015 | Seminole | Seminole County | Indoor Pluming | Indoor Plumbing Rebate Program | 93004 | 46502.4 | 4.2 | 11506.8493 | 939 | 1.4 | closed | yes | completed
SWFWMD | N714 | 2016 | Polk | Polk County Utilities | Irrigation | Landscape and irrigation evaluation Program | 55000 | 27500 | 10.22 | 28000 | 500 | 1.31 | 2018-11-30 | yes | Ongoing | 200 irrigation system evaluations, estimated savings is 140 gpd each, cost is $200 each. Approximately 100 rain sensor devices installed at $75 each. Also included are educational materials, program promotion, and surveys necessary to ensure the success of the program. Approximately 200 conservation kits will also be provided $10 each.
SWFWMD | N716 | 2016 | Polk | Polk County Utilities | software AMA | Customer Portal Pilot Project | 20000 | 10000 | 32.85 | 90000 | 5000 | 0.06 | 2018-03-01 | no | Ongoing | The project consists of a pilot program for an online software program that will enable effective distribution of conservation information. 5,000 accounts
SJRWMD |  | 2016 | Orange | City of Apopka | Irrigation | ET controllers, nozzles landscapes | 140176 | 70088 |  | 0 |  | 1.08 | open | Yes | 3 yr pre and past data will be submitted. | 36.64% savings based on pilot phase.
SJRWMD |  | 2016 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 111470 | 55735 |  | 0 | 500 | 3.38 | open | NO | Meter replacement only , no software
SJRWMD |  | 2016 | Orange | OCU | Indoor Pluming | Toilet retrofit | 20000 | 10000 | 1.7 | 4657.5342 | 200 | 0.8 | Open | yes | Start in fall 2016 200 toilets replaced | should end by 9/17
SJRWMD |  | 2016 | Orange | OCU | Indoor outdoor | Waterwise Neighbor Program | 21830 | 10915 | 6.1 | 16712.3288 | 100 | 0.78 | Open | Yes | starts in Fall 100 homes targeted in Wekiva basin
SJRWMD |  | 2016 | Orange | OCU | Irrigation | Rainsensor Replacement Project | 97.945 | 49150 | 35.73 | 97890.411 | 1100 | 1 | open | No | replace 1,100 rainsensors predicts 15K/month | $107.25mg for the life of the devise
SJRWMD |  | 2016 | Orange | OCU | software AMA | Water$mart Customers Conserve | 224668 | 112334 | 134.9 | 369589.0411 | 30000 | 0.36 | open | No | Community based social marketing to reduce use. | 4.9% savings expected
SJRWMD |  | 2016 | Orange | OUC | Irrigation | High Water Use Target Conservation | 786044 | 369397 | 405.9 | 1112054.7945 | 4847 | 0.71 | Open | Yes | Retrofit high use homes outdoor use | Using PREC tool to measure savings
SFWMD | WC-2010 | 2017 | Osceola | Toho Water Authority | ALFDs | Automatic Line Flushing Devices | 200000 | 76500 | 23.2 | 63561.6438 | 30 | 1.1 | On Schedule | no | Contract has not been executed for this project | Install 30 automatic line flushing devices at computer modeled locations with high water age, thereby maintaining high water quality and reducing the amount of water wasted during flushing activities.
SFWMD | WC-2015 | 2017 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 47000 | 23500 | 3.42 | 9369.863 | 300 | 0.58 | On Schedule | yes | Contract has not been executed for this project | This program will provide 300 rebates of $145 each to homes within the City of St. Cloud service area toward the purchase and installation of any WaterSense HET and all associated hardware.
SFWMD | WC-2023 | 2017 | Orange | Orange County Utilities | Software | Water Conservation Software Technology Project for Southwest Orange County | 169981 | 50990 | 162.6 | 445479.4521 | 0 | 1.08 | On Schedule | no | Contract has not been executed for this project | Orange County Utilities will contract with WaterSmart Software Inc. to implement software that combines technology and community-based social marketing to reduce potable water consumption of 24,283 households.
SFWMD | WC-2027 | 2017 | Polk | Polk County BOCC | Software | Water Conservation Software Technology for Oak Hills water use area | 205920 | 60000 | 5.2 | 14246.5753 | 0 | 3.3 | On Schedule | no | Contract has not been executed for this project | Installation of AMI hardware and a software component for leak notification, water use comparison, historical use, threshold alarms, 2-way messaging between utility and customers, and report generation.
SWFWMD | N820 | 2017 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation program | 82800 | 41400 | 15.33 | 42000 | 300 | 1.31 |  | yes | Ongoing | 300 irrigation system evaluations. Approximately 150 rain sensor devices installed. Also included are educational materials, program promotion, follow-up evaluations, and surveys necessary to ensure the success of the program. Approximately 300 conservation kits
SWFWMD | N814 | 2017 | Polk | Polk County Utilities | software AMA | Customer portal project | 300000 | 150000 | 153.47 | 420465.7534 | 60000 | 1.95 |  | no | Ongoing | Full implementation of an online software program that will enable more effective distribution of conservation information and activities. This also includes a utility side dashboard. The software and promotion material will be utility wide (approximately 60,000 accounts) for approximately one year. The demand reduction of approximatly 3%
SWFWMD | P921 | 2017 | Polk | PRWC | Indoor Pluming | indoor retrofit | 242550 | 121275 | 31.89 | 87370 | 3135 | 0.48 | 2019-10-01 | yes | Ongoing | FDEP funded project. 1,830 toilet rebates to replace 3.5 gpf or higher models with WaterSense labeled fixtures (1.28 gpf). 1,305 conservation kits to be distributed to homeowners.
SWFWMD | P920 | 2017 | Polk | PRWC | Irrigation | outdoor BMPs | 332150 | 166075 | 19.0895 | 52300 | 872 | 1.8 | 2019-10-02 | yes | Ongoing | FDEP funded project. 49 FFL rebates to change high water-use landscapes into a Florida Friendly area that requires minimal irrigation and chemicals; 229 smart irrigation (ET) controllers installed by a licensed contractor and education on proper unit operation; 594 wireless rain sensors
SWFWMD | P922 | 2017 | Polk | PRWC | FL waterstar rebates | Florida water star rebates | 700000 | 350000 | 24.1502 | 66165 | 500 | 2.02 | 2019-10-03 | no | Ongoing | FDEP funded project. 500 rebates to be distributed to new home builders within Polk County who build homes to Florida Water Star standards and submits proof of Water Star certification. $700 rebate per home
SJRWMD |  | 2017 | Orange | City of Apopka | Irrigation | Nozzle replacement | 140000 | 70000 | 44.5 | 121917.8082 | 200 | 0.832 | open | No | Expect 30 - 50% savings over 200 plus audits. | based on cost shar eapplication
SJRWMD |  | 2017 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 2230565.4 | 1115283 | 153.3 | 420000 | 9000 | 1.1 | open | No | Expansion of existing AMI program which has proven successful to engage homeowners to conserve.
SJRWMD |  | 2017 | Orange | OCU | Whole house | Waterwise Neighbor Retrofit | 74808 | 37404 | 9.9 | 27123.2877 | 300 | 6.01 | open | Yes | Retrofit high water users indoors and out | Pre and post water use data will be required.
SJRWMD |  | 2017 | Orange | OCU | Whole House | Waterwise Neighbor NEW | 271962.5 | 135981.25 | 30.2 | 82739.726 | 500 | 3.75 | open | Yes | Partner with builders to build water efficient homes | 82,967 gpd referenced in application so 30.2 MGY.
SJRWMD | 27269 | 2017 | Orange | Winter Garden | AMR implementation | AMR meter replacement | 400000 | 200000 | 14.3 | 39178.0822 | 1187 | 2.33 | open | No | Expand existing AMR to more homes

## 2010-2013
District | Project # or ID number | Fiscal Year | County | Entity Alias | Project Type | Project Title | Actual Project Cost/ Est. Project Cost1 | Actual Funding/ Approved Funding1 | Water Savings (MGY)2 | Water Savings (GPD) | Number of Implementations1 | Cost effectiveness per Kgal | Status | Is project a quantified BMP? Yes / No | Comments | Background
SWFWMD | N112 | 2010 | Polk | Lakeland | Indoor Pluming | Toilet Rebate Program | 143702.3 | 70097.62 | 8.6279 | 23638 | 753 | 1.01 | 2011-07-19 | yes | complete | average savings of 31.4 gal per per day per fixture
SWFWMD | N221 | 2010 | Polk | Winter Haven | Irrigation | Smart Irrigation Controller Pilot Project | 7900 | 3950 | 7.8413 | 21483 | 12 | 0.09 | 2012-10-26 | yes | complete | low participation, only 12 of expected 50 SMS were installed. A single contractor was hired to install the SMS
SFWMD | - | 2011 | Orange | Orange County Utilities | Indoor plumbing | Commercial Showerhead Retrofit | 48011.28 | 23822.45 | 57.85 | 158493.1507 | 16443 | 0.03 | Closed | yes | Due to lower fixture costs, project exceeded original estimates. Actual installations, 5,795 showerheads (188%) and 10,648 aerators (307%) | Purchase, distribute and verify installation of 3,075 commercial grade 1.5 gpm fixed and/or handheld showerheads, and 3,465 commercial grade 1 gpm faucet aerators in three commercial properties located along the I-4 corridor.
SWFWMD | N249 | 2011 | Polk | Frostproof | Indoor Pluming | Toilet Rebate Program | 1954 | 977 | 0.1971 | 540 | 20 | 1.16 | 2013-10-15 | yes | complete | low participation, only 20 of expected 50 rebates were done.
SWFWMD | N314 | 2011 | Polk | Lake Alfred | Indoor Pluming | Toilet Rebate Program/DIY | 16200 | 8100 | 2.8488 | 7805 | 557 | 0.57 | 2013-10-24 | yes | complete | high participation, 57 of expected 50 rebates. Also 500 conservation kits (showerhead, aerators)
SFWMD | - | 2012 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33639.6 | 14500 | 2.28 | 6246.5753 | 217 | 0.62 | Closed | yes | Project is 100% complete. Project exceeded 200 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of an EPA WaterSense high efficiency toilet, on participants utility bill.
SWFWMD | N363 | 2012 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 1 | 41378 | 20689 | 10.646 | 29167 | 211 | 0.95 | 2015-12-31 | yes | complete | low participation, 211 of expected 1,100 irrigation evals. Contractor, and participation issues. An averagae of 138 gpd savings at each home based on final report 1 year pre and post monitoring. 287 conservation kits were also distributed.
SJRWMD | 27338 | 2012 | Orange | City of Ocoee | AMI | Installed smart meters educated public to monitor use | 132367 | 66184 | 3.1 | 8493.1507 | 390 | 5.03 | Closed | No | 7-11% reduction in neighborhoods with meters. | https://www.youtube.com/watch?v=80joid0XJn4 20 yr life on meters. Contract required 3 years data pre and post
SJRWMD | 27285 | 2012 | Orange | City of Apopka | Irrigation | Rebate to 100 customers to install ET controllers | 35000 | 17500 | 1.3 | 3561.6438 | 100 | 1.58 | Closed | yes | 3 yr pre post data showed 35% - 50% reduction/month
SJRWMD | 27287 | 2012 | Orange | City of Apopka | Irrig.Enforcement | Landscape implementation Ordinance Implementation | 64000 | 32000 |  | 0 |  | NA | Closed | No | 3 year pre and post data but no analysis. | Scope included assistance to city to identify violation, work with homeowners on reason and perform audits. 3 yr pre and post data.3/31/13 completion.
SJRWMD | 25435 | 2012 | Orange | Orange County | Irrigation | Smart controller study | 230000 | 100000 |  | 0 |  | NA | Closed | yes | Contract paid out | Results show 30 - 60% savings
SJRWMD | 27288 | 2012 | Orange | City of Apopka | AMI | AMI implementation Program | 79450 | 39725 |  | 0 |  | NA | Closed | No | AMI Software update and report analysis
SJRWMD | 26804 | 2012 | Lake | City of Groveland | Outreach | Irrigation Rule enforcement | 98460 | 48230 |  | 0 |  | NA | closed | No | Consumption data not submittedin this contract. | Contract was to do irrigation enforcement and education.
SFWMD | - | 2013 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program | 40000 | 20000 | 3.87 | 10602.7397 | 320 | 0.44 | Closed | yes | 100% complete. | Approve, process, and apply 320 (up to) $125 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SFWMD | - | 2013 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 18451.28 | 9000 | 1.14 | 3123.2877 | 114 | 0.68 | Closed | yes | 100% complete. | Approve, process, and apply 100 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet, with a limit of one (1) per residential dwelling unit, on participants’ utility bill
Total | [6 empty] | 990513.46 | 474775.07 | 99.701 | 273153.5479 | 19137
Quantified BMPs only | [6 empty] | 616236.46 | 288636.07 | 96.601 | 264660.3973 | 18747
Total yellow highlighted-not quantified with survey | [9 empty] | 8493.1507

## 2014-2015
District | Project # or ID number | Fiscal Year | County | Entity Alias | Project Type | Project Title | Actual Project Cost/ Est. Project Cost1 | Actual Funding/ Approved Funding1 | Water Savings (MGY)2 | Water Savings (GPD) | Number of Implementations1 | Cost effectiveness per Kgal | Status | Is project a quantified BMP? Yes / No | Comments | Background
SFWMD | - | 2014 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 2.5 | 6849.3151 | 207 | 0.51 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and apply 207 (up to) $145 rebates, for the purchase and installation of all associated hardware per WaterSense labeled high efficiency toilet, with a limit of two per residential dwelling unit, on the participants’ utility bill
SJRWMD | 28091 | 2014 | Orange | OCU | Irrigation | Nozzle replacement | 94350 | 31135 | 24 | 65753.4247 | 143 | NA | Closed | No | 5000 nozzles in 143 residences installed by 9/15 | No pre and post data required.
SFWMD | - | 2015 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 33015.61 | 16500 | 2.3 | 6301.3699 | 224 | 0.61 | Closed | yes | 100% complete. Processed 224 rebates. | Approve, process, and apply 200 (up to) $145 rebates, for the purchase and installation of all associated hardware for any WaterSense labeled high efficiency toilet with a UNAR Map rating above 400 grams per flush, with a limit of one (1) per residential dwelling unit, on participants' utility bill
SFWMD | - | 2015 | Osceola | Toho Water Authority | Indoor plumbing | Toilet Rebate Program 2013-2014 | 30015 | 15000 | 1.25 | 3424.6575 | 207 | 1.01 | Closed | yes | 100% complete. Processed 207 rebates at $145 each for the purchase and installation of HETs | Approve, process, and pay 207 rebates at $145 high efficiency toilet, with a limit of two (2) per eligible residential dwelling units within the Toho Water Authority service area
SWFWMD | N613 | 2015 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation Program - Phase 2 | 44170 | 22085 | 11.899 | 32600 | 222 | 0.84 | 2016-08-31 | yes | Ongoing | costs are $155 per evaluation plus $75 for rain sensor install.
SJRWMD | 26655 | 2015 | Seminole | City of Sanford | AMR | Installation of meters and software | 490000 | 245000 |  | 0 |  | NA | closed | No | UF report on results Dr Heaney. | 1.7mgd at a cost of $8.5 million 15 yr useful life 11% reduction in water loss.
SJRWMD | 27296 | 2015 | Seminole | Seminole County | Indoor Pluming | Indoor Plumbing Rebate Program | 93004 | 46502.4 | 4.2 | 11506.8493 | 939 | 1.4 | closed | yes | completed
Total | [6 empty] | 814569.61 | 391222.4 | 46.149 | 126435.6164 | 1942
Quantified BMPs only | [6 empty] | 230219.61 | 115087.4 | 22.149 | 60682.1918 | 1799
Total yellow highlighted-not quantified with survey | [9 empty] | 65753.4247

## 2016 +
District | Project # or ID number | Fiscal Year | County | Entity Alias | Project Type | Project Title | Actual Project Cost/ Est. Project Cost1 | Actual Funding/ Approved Funding1 | Water Savings (MGY)2 | Water Savings (GPD) | Number of Implementations1 | Cost effectiveness per Kgal | Status | Is project a quantified BMP? Yes / No | Comments | Background
SWFWMD | N714 | 2016 | Polk | Polk County Utilities | Irrigation | Landscape and irrigation evaluation Program | 55000 | 27500 | 10.22 | 28000 | 500 | 1.31 | 2018-11-30 | yes | Ongoing | 200 irrigation system evaluations, estimated savings is 140 gpd each, cost is $200 each. Approximately 100 rain sensor devices installed at $75 each. Also included are educational materials, program promotion, and surveys necessary to ensure the success of the program. Approximately 200 conservation kits will also be provided $10 each.
SWFWMD | N716 | 2016 | Polk | Polk County Utilities | software AMA | Customer Portal Pilot Project | 20000 | 10000 | 32.85 | 90000 | 5000 | 0.06 | 2018-03-01 | no | Ongoing | The project consists of a pilot program for an online software program that will enable effective distribution of conservation information. 5,000 accounts
SJRWMD |  | 2016 | Orange | City of Apopka | Irrigation | ET controllers, nozzles landscapes | 140176 | 70088 |  | 0 |  | 1.08 | open | Yes | 3 yr pre and past data will be submitted. | 36.64% savings based on pilot phase.
SJRWMD |  | 2016 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 111470 | 55735 |  | 0 | 500 | 3.38 | open | NO | Meter replacement only , no software
SJRWMD |  | 2016 | Orange | OCU | Indoor Pluming | Toilet retrofit | 20000 | 10000 | 1.7 | 4657.5342 | 200 | 0.8 | Open | yes | Start in fall 2016 200 toilets replaced | should end by 9/17
SJRWMD |  | 2016 | Orange | OCU | Indoor outdoor | Waterwise Neighbor Program | 21830 | 10915 | 6.1 | 16712.3288 | 100 | 0.78 | Open | Yes | starts in Fall 100 homes targeted in Wekiva basin
SJRWMD |  | 2016 | Orange | OCU | Irrigation | Rainsensor Replacement Project | 97.945 | 49150 | 35.73 | 97890.411 | 1100 | 1 | open | No | replace 1,100 rainsensors predicts 15K/month | $107.25mg for the life of the devise
SJRWMD |  | 2016 | Orange | OCU | software AMA | Water$mart Customers Conserve | 224668 | 112334 | 134.9 | 369589.0411 | 30000 | 0.36 | open | No | Community based social marketing to reduce use. | 4.9% savings expected
SJRWMD |  | 2016 | Orange | OUC | Irrigation | High Water Use Target Conservation | 786044 | 369397 | 405.9 | 1112054.7945 | 4847 | 0.71 | Open | Yes | Retrofit high use homes outdoor use | Using PREC tool to measure savings
SFWMD | WC-2010 | 2017 | Osceola | Toho Water Authority | ALFDs | Automatic Line Flushing Devices | 200000 | 76500 | 23.2 | 63561.6438 | 30 | 1.1 | On Schedule | no | Contract has not been executed for this project | Install 30 automatic line flushing devices at computer modeled locations with high water age, thereby maintaining high water quality and reducing the amount of water wasted during flushing activities.
SFWMD | WC-2015 | 2017 | Osceola | St. Cloud | Indoor plumbing | Toilet Rebate Program | 47000 | 23500 | 3.42 | 9369.863 | 300 | 0.58 | On Schedule | yes | Contract has not been executed for this project | This program will provide 300 rebates of $145 each to homes within the City of St. Cloud service area toward the purchase and installation of any WaterSense HET and all associated hardware.
SFWMD | WC-2023 | 2017 | Orange | Orange County Utilities | Software | Water Conservation Software Technology Project for Southwest Orange County | 169981 | 50990 | 162.6 | 445479.4521 | 0 | 1.08 | On Schedule | no | Contract has not been executed for this project | Orange County Utilities will contract with WaterSmart Software Inc. to implement software that combines technology and community-based social marketing to reduce potable water consumption of 24,283 households.
SFWMD | WC-2027 | 2017 | Polk | Polk County BOCC | Software | Water Conservation Software Technology for Oak Hills water use area | 205920 | 60000 | 5.2 | 14246.5753 | 0 | 3.3 | On Schedule | no | Contract has not been executed for this project | Installation of AMI hardware and a software component for leak notification, water use comparison, historical use, threshold alarms, 2-way messaging between utility and customers, and report generation.
SWFWMD | N820 | 2017 | Polk | Polk County Utilities | Irrigation | Landscape and Irrigation Evaluation program | 82800 | 41400 | 15.33 | 42000 | 300 | 1.31 |  | yes | Ongoing | 300 irrigation system evaluations. Approximately 150 rain sensor devices installed. Also included are educational materials, program promotion, follow-up evaluations, and surveys necessary to ensure the success of the program. Approximately 300 conservation kits
SWFWMD | N814 | 2017 | Polk | Polk County Utilities | software AMA | Customer portal project | 300000 | 150000 | 153.47 | 420465.7534 | 60000 | 1.95 |  | no | Ongoing | Full implementation of an online software program that will enable more effective distribution of conservation information and activities. This also includes a utility side dashboard. The software and promotion material will be utility wide (approximately 60,000 accounts) for approximately one year. The demand reduction of approximatly 3%
SWFWMD | P921 | 2017 | Polk | PRWC | Indoor Pluming | indoor retrofit | 242550 | 121275 | 31.89 | 87370 | 3135 | 0.48 | 2019-10-01 | yes | Ongoing | FDEP funded project. 1,830 toilet rebates to replace 3.5 gpf or higher models with WaterSense labeled fixtures (1.28 gpf). 1,305 conservation kits to be distributed to homeowners.
SWFWMD | P920 | 2017 | Polk | PRWC | Irrigation | outdoor BMPs | 332150 | 166075 | 19.0895 | 52300 | 872 | 1.8 | 2019-10-02 | yes | Ongoing | FDEP funded project. 49 FFL rebates to change high water-use landscapes into a Florida Friendly area that requires minimal irrigation and chemicals; 229 smart irrigation (ET) controllers installed by a licensed contractor and education on proper unit operation; 594 wireless rain sensors
SWFWMD | P922 | 2017 | Polk | PRWC | FL waterstar rebates | Florida water star rebates | 700000 | 350000 | 24.1502 | 66165 | 500 | 2.02 | 2019-10-03 | no | Ongoing | FDEP funded project. 500 rebates to be distributed to new home builders within Polk County who build homes to Florida Water Star standards and submits proof of Water Star certification. $700 rebate per home
SJRWMD |  | 2017 | Orange | City of Apopka | Irrigation | Nozzle replacement | 140000 | 70000 | 44.5 | 121917.8082 | 200 | 0.832 | open | No | Expect 30 - 50% savings over 200 plus audits. | based on cost shar eapplication
SJRWMD |  | 2017 | Orange | City of Ocoee | AMI | AMI Meter Upgrade | 2230565.4 | 1115283 | 153.3 | 420000 | 9000 | 1.1 | open | No | Expansion of existing AMI program which has proven successful to engage homeowners to conserve.
SJRWMD |  | 2017 | Orange | OCU | Whole house | Waterwise Neighbor Retrofit | 74808 | 37404 | 9.9 | 27123.2877 | 300 | 6.01 | open | Yes | Retrofit high water users indoors and out | Pre and post water use data will be required.
SJRWMD |  | 2017 | Orange | OCU | Whole House | Waterwise Neighbor NEW | 271962.5 | 135981.25 | 30.2 | 82739.726 | 500 | 3.75 | open | Yes | Partner with builders to build water efficient homes | 82,967 gpd referenced in application so 30.2 MGY.
SJRWMD | 27269 | 2017 | Orange | Winter Garden | AMR implementation | AMR meter replacement | 400000 | 200000 | 14.3 | 39178.0822 | 1187 | 2.33 | open | No | Expand existing AMR to more homes
Total | [6 empty] | 6777022.845 | 3313527.25 | 1317.9498 | 3610821.3014 | 118571
Quantified BMPs only | [6 empty] | 2074320.5 | 1013535.25 | 533.7496 | 1462327.5342 | 11054
2275069.1096
Total yellow highlighted-not quantified with survey

## Summary
| 2010-2013 | 2014-2015 | 2016+ | Total
savings gpd, All | 273153.5479 | 126435.6164 | 3610821.3014 | 4010410.4658
savings gpd, quantified BMPs only | 264660.3973 | 60682.1918 | 1462327.5342 | 1787670.1233